## Overview
By June 10, you should have:
A validated brand concept
Clear first product(s) defined
Supplier/manufacturer path chosen
Early audience + proof of demand
Content system running
Advisors + industry contacts
Operational clarity

## 6-Month Brand Roadmap
| # | Phase | Task Category | Task Description | SMART Goal | Output / Success Metric | Start Date | Deadline | Priority | Estimated Weekly Hours | Status | Notes / Links
| 1 | Phase 1: Foundation | Brand Strategy | Define Brand DNA & Positioning | By Jan 14, complete a clear 1–2 page Brand DNA document defining purpose, vision, values, target customer psychographics, competitive landscape, and price/quality positioning. | Completed Brand DNA document ready to share with advisors or collaborators | 2026-01-07 | 2026-01-14 | High | 3 | In Progress
| 2 | Phase 1: Foundation | Product Strategy | Identify launch product categories | By Jan 21, select 1–2 hero product categories with clear customer problem, usage occasion, expected retail price, and reason for launch relevance. | Launch Product Thesis (1-page) with category, price range, and rationale | 2026-01-14 | 2026-01-21 | High | 3 | In Progress | Jacket, trousers, and shirt
| 3 | Phase 1: Foundation | Product Strategy | Blank vs Cut-and-Sew decision | By Jan 28, evaluate blanks vs cut-and-sew across cost, timeline, differentiation, MOQs, and brand integrity, and document final decision. | Written production decision with rationale and next steps | 2026-01-21 | 2026-01-28 | High | 2 | In Progress | cut and sew
| 4 | Phase 1: Foundation | Market Research | Market demand validation | By Feb 2, conduct 15–20 customer interviews, distribute one survey with 50+ responses, and launch a basic waitlist landing page. | 30%+ of respondents indicate likely purchase at target price; waitlist live | 2026-01-21 | 2026-02-02 | High | 4 | Not Started
| 5 | Phase 2: Audience | Brand Story | Develop founder & brand story | By Feb 9, articulate founder story, brand worldview, core message, and three repeatable brand pillars for use across content and marketing. | Finalized brand narrative document | 2026-02-03 | 2026-02-09 | High | 2 | Not Started
| 6 | Phase 2: Audience | Marketing Setup | Launch social media & email list | By Feb 16, create and optimize Instagram, TikTok, and email list with consistent handles, bios, and brand positioning. | Live social profiles + functioning email signup | 2026-02-10 | 2026-02-16 | High | 2 | Not Started
| 7 | Phase 2: Audience | Content | Plan content series & calendar | By Mar 2, define three content series, posting cadence, formats, and create a 30-day content calendar. | 30-day content calendar completed | 2026-02-17 | 2026-03-02 | High | 3 | Not Started
| 8 | Phase 3: Product | Sourcing | Supplier & manufacturer outreach | By Mar 16, identify 10–15 suppliers or manufacturers, initiate outreach, and maintain at least five active conversations. | Supplier comparison sheet with MOQ, pricing, lead times | 2026-03-03 | 2026-03-16 | High | 4 | Not Started
| 9 | Phase 3: Product | Product Dev | Finalize product specs & sampling plan | By Mar 30, define fabric, fit references, construction details, size run, sampling costs, and timeline. | Complete product spec sheet + confirmed unit economics | 2026-03-17 | 2026-03-30 | High | 4 | Not Started
| 10 | Phase 4: Validation | Community | Engage online communities | From Mar 10 to May 1, consistently participate in 2–3 relevant communities weekly with thoughtful, non-promotional engagement. | Recognizable presence and recurring interactions in communities | 2026-03-10 | 2026-05-01 | Medium | 2 | Not Started
| 11 | Phase 4: Validation | Growth | Audience growth benchmarks | By May 1, grow to 500+ Instagram followers or 200+ email subscribers with 5%+ engagement. | Follower/subscriber targets met with engagement benchmarks | 2026-04-07 | 2026-05-01 | High | 3 | Not Started
| 12 | Phase 4: Validation | Sales Test | Soft launch or preorder test | By May 11, run a preorder, waitlist incentive, or limited paid drop to test willingness to pay. | 10–20 paying customers or deposits collected | 2026-04-21 | 2026-05-11 | High | 3 | Not Started
| 13 | Phase 5: Transition | Finance | Quit-readiness financial check | By May 25, confirm 6–9 months personal runway, brand budget, and post-June revenue plan. | Documented runway and budget confirmation | 2026-05-12 | 2026-05-25 | High | 2 | Not Started
| 14 | Phase 5: Transition | Advisors | Build informal board of advisors | By June 1, secure 2–3 experienced advisors and establish a recurring check-in cadence. | Confirmed advisors with scheduled check-ins | 2026-05-15 | 2026-06-01 | Medium | 2 | In Progress
| 15 | Phase 5: Transition | Decision | Final go/no-go decision | By June 10, evaluate traction, finances, and confidence to make a clear decision to quit or delay strategically. | Documented go/no-go decision with rationale | 2026-06-01 | 2026-06-10 | High | 1 | Not Started
x | x

## List Inputs
High
Medium
Low
Not Started
In Progress
Done